## Sheet1
Sl No | Issue Name | Issue Desc | Status | Priority | Comment
1 | Setup of WiFi Credentials and cloud DB update for Switch Controllers | Current iteration of the mobile app is capable, but UX can be improved upon. | Not Started | Medium | This is a backend issue which needs to be addressed ]
2 | Setup of WiFi Credentials and cloud DB update for Touch Switchboard | Setup flow for Switch Controllers is used instead. This limits the functionality of Touch Switchboard | Not Started | High | This is a backend issue which needs to be addressed ]
3 | New UI Element for Fan Speed Controller | Switch Controllers do not support fan speed control but Touch Switchboards do. Hence, this UI element is required. | Completed | Critical | Api for fan controller
4 | New UI Element for Touch Switch Illumination On/Off | Touch Switch panels are illuminated for visibility and hence need to be toggled On / Off. | Completed | Low | API for touch switch
5 | Support for Up To 16 Switch Modules | Switch Controllers support 8 Switches per module. Touch switches support up to 16 | Issue Cancelled | Critical | There is no need to develop the same
6 | New UI Element for Group Control | Currently, switches grouped together are toggled On/Off. Add On / Off button instead. | Completed | High | API required
7 | Improve Group Control UX | Group control is only reliant on local data for the state of groups. This is slow and impacts UX. Hence, cloud must be used for state retrieval and local data must be used for verification / correction. | Issue Cancelled | High | This is issue is cancelled as it is addressed in the previous issue
8 | Fix Blinking Issue | Toggle buttons for switches blink when they retrieve / receive state. This is observed typically in android and must be fixed. | Completed | HIgh
9 | Allow user to toggle switches simultaneously | A loading popup blocks the user from toggling switches On/Off currently. New update must allow the user to tap on multiple buttons and the app must send a signal accordingly. | Working | High | There should be a simplete on off swith which will the group devices
10 | Automation Page access and management via cloud | Users must be able to view / modify automations such as timers, schedulers via cloud as well. | Working | Medium | API Integration pending
11 | Add a per second limit to requests made by a client. | Multiple requests made due to technical glitches overload the server and use up valuable server resources. A solution must be figured out for this issue | Not Started | High | This is should be done in the server
12 | Apple HomeKit Compatibility for Touch Switches and Switch Controller | Update must be compliant and be able to pass the certification test for apple homekit | Issue Cancelled | Low | Not Required
13 | Access to multiple homes per user | Update must allow users to join, create, manage multiple homes | Issue Cancelled | Medium | Need for later
14 | Delete & Edit Slots, Rooms, Switch Controllers, Touch Switches, Home | Update must allow users to Slot Name & icon, room name & icon, switch controller name & icon, touch switches name & icon, home name and accounts linked | Completed | High | API required
15 | New UI element for 2 way switches | Touch switches do not support viewing state of 2 way switches. Hence, a new UI element that does not show any state must be designed for 2 way | Completed | Critical | API Required
16 | Voice Assistant support for Fan speed control | The current version of the server does not support fan speed control. Hence, app update must allow fan speed control | Not Started | Critical | The files will be sent and the same should be appended with few minor changes and access should be given for alexa
17 | Inverted UI colours on some devices | It is observed that the colours in the app are inverted when the app is opened on some devices and hence must be rectified | Completed | High | Issues is being addessed